## Sheet1
| WDD_Project_2023 | Done Y/N? | Team Member
Week | Goals for this week
week 8
| read brief & be familiar with it | Yes | Oisin
| brainstorm with group - what is website like | Yes | Oisin
| team member strengths and weaknesses | Yes | Oisin
| 1 person creates a shared folder and shares it! | Yes | Oisin
| my own wireframe | Yes | Oisin
week 9 | use wireframe to code up page | Yes | Oisin
| think about class and id names so no-one overwrites anothers CSS! | Yes | Oisin
| decide who does the form/gallery/minigame | Yes | Oisin
| decide website content | Yes | Oisin
| record who contributed - meeting and coding | Yes | Oisin
| Let Emer know if someone is out of contact | Yes | Oisin
week 10 | add your tasks and assign them to a team member | Yes | Oisin
| Let Emer know if someone is out of contact | Yes | Oisin
week 11 | add your tasks and assign them to a team member | Yes | Oisin
| Let Emer know if someone is out of contact | Yes | Oisin
week 12 | finish up code | Yes | Oisin
| deploy website | Yes | Oisin
| testing - functional testing, speed test | Yes | Oisin
| Write/record report | Yes | Oisin
Submission | SUNDAY 10th DEC 11pm
| decide who does this | Yes | Oisin