## Sheet1
| WDD_Project_2023 | Done Y/N? | Team Member
Week | Goals for this week
week 8
read brief & be familiar with it
brainstorm with group - what is website like
team member strengths and weaknesses
1 person creates a shared folder and shares it!
my own wireframe
week 9 | use wireframe to code up page
think about class and id names so no-one overwrites anothers CSS!
decide who does the form/gallery/minigame
decide website content
record who contributed - meeting and coding
Let Emer know if someone is out of contact
week 10 | add your tasks and assign them to a team member
Let Emer know if someone is out of contact
week 11 | add your tasks and assign them to a team member
Let Emer know if someone is out of contact
week 12 | finish up code
deploy website
testing - functional testing, speed test
Write/record report
Submission | SUNDAY 10th DEC 11pm
decide who does this